## A
OSCEOLA CREEK MIDDLE SCHOOL (99-HH)
CONSTRUCTION MANAGEMENT AT RISK PROJECT
PROJECT #2821-8192
HISTORY:
2002-08-21 | Board Report 13D-3 for a Re-use Agreement with BRPH Companies in the amount of $650,000.00 for Acreage Area Middle School (99-HH)
2002-10-16 | Board Report 13D-4 for an Agreement for CM@Risk Services and Pre-Construction fees of $61,100.00 to James A. Cummings.
2003-01-22 | Board Report 13D-8 for Amendment #1 to the Agreement establishing the GMP of $19,235,306.00 to James A. Cummings, Inc.
2003-02-14 | Notice-to-Proceed
487 | Original Contract Days | [7 empty] | ATTACHMENT
2004-06-15 | Original Substantial Completion
2004-07-15 | Original Final Completion | [7 empty] | Board Report 12B-4
2004-06-25 | Actual Substantial Completion | [7 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD) |  |  | 30
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  |  | A | C | D | E | L | M | P | S | U | Z
| 12B-11 | 2003-01-22 |  |  |  |  | - | Agreement in the amount of $198,061.50 with the Seminole Improvement District for the provision of potable water at new school site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-1 | 2004-04-21 |  |  | 18700 |  | Z | Additional Architectural Services to define, design, and construct a new wetlands area at the school site to replace the wetlands area, which was destroyed during the construction process. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-1 | 2004-05-19 |  |  | 8206 |  | Z | Additional Architectural Services to provide Construction Administration for the construction of turn lane and other necessary road improvements to facilitate the operations at the new school. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 12C-2 | 2004-05-19 | 137368 |  |  |  | S | CCD #1 - Provide and install all conduit and cabling to facilitate the installation of ceiling projection components and equipment. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137368 | 0 | 0
1 | 12C-2 | 2004-05-19 | 30409 |  |  |  | S | CCD #3 - Clear, grub, elevate, irrigate, sod and fence the 2.5 acre site of the north east corner of the site which was originally designated as a Palm Beach County Sheriff’s Station. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30409 | 0 | 0
1 | 12C-2 | 2004-05-19 | 128324 |  |  |  | Z | CCD #4 - Construction of turn lanes, drainage facilities and other road improvements to facilitate the safe flow of traffic at the new middle school. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128324
2 | 12C-2 | 2004-08-18 | -100000 |  |  |  | S | CCD #5 - Deduct $100,000.00 from the Contractors contract for transfer of funds to the Furniture Fixture and Equipment Account. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0
| 12B-4 | 2004-12-08 |  |  |  |  | - | Reduction of Retainage from 10% to 5% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 196101 | 0 | 26906 | 0
|  | ORIG SUM | 19296406 |  | 650000
|  | REV SUM | 19492507 |  | 676906
|  | % CO'S | 1.016% |  | 4.139% | 0%
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | 0% |  |  | M = Mandatory | 0 | 0%
C = Contractor Suggested |  |  | 0 |  | 0% |  |  | P = Principal Requested | 0 | 0%
D = Design Omission |  |  | 0 |  | 0% |  |  | S = School District Requested | 67777 | 0.3512%
E = Design Error |  |  | 0 |  | 0% |  |  | U = Unforeseen Conditions | 0 | 0%
L = Liquidated Damages |  |  | 0 |  | 0% |  |  | Z = Outside Agency | 128324 | 0.665%