## A
PLEASANT CITY ELEMENTARY SCHOOL
DESIGN/BUILD PROJECT
PROJECT #2591-8171
HISTORY:
2001-06-20 | Board Report 13D-1 for approval of Award of Contract to The Haskell Company in the amount of $7,607,700 for Design/Build
2001-10-21 | Notice-to-Proceed
368 | Original Contract Days
2002-09-24 | Original Substantial Completion
2002-10-24 | Original Final Completion
5 | Extensions to Date
0 | Extension this item
2002-09-29 | Revised Substantial Completion | [8 empty] | ATTACHMENT
2002-10-29 | Revised Final Completion
2003-09-10 | Actual Substantial Completion | [8 empty] | Board Report 12B-7
2003-10-10 | Actual Final Completion | [8 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD)
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  | A | C | D | E | L | M | P | S | U | Z
1 | 12B-5 | 2002-02-20 | 56596 |  |  |  | S | CCD #1 - Install laminated glass on the first floor windows of the entire structure. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56596 | 0 | 0
2 | 12B-8 | 2002-02-20 | 30908 |  |  |  | S | COPR #1 - Excavate and abandon and replace the water line. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30908 | 0 | 0
3 | 12B-9 | 2002-02-20 | 3760 |  |  |  | U | COPR #2 - Re-design the drainage system on the campus. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3760 | 0
4 | 12B-10 | 2002-02-20 | 24825 |  |  |  | S | COPR #3 - The Department of Maintenance and School Police have designed a new door system for the exterior of schools. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24825 | 0 | 0
5 | 12B-5 | 2002-03-13 | 17200 |  |  |  | S | COPR #5 - Restore the asphalt shingles. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17200 | 0 | 0
| 12B-1 | 2002-05-15 | 20500 | 5 |  |  | S | NTE CCD #2 - Perform exploratory excavation of Dixie Highway for installation of proposed sewer water tie-ins, and determine whether there is sufficient space for the placement of our sanitary structure. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20500 | 0 | 0
6 | 12B-10 | 2002-07-17 | -5270 |  |  |  | S | CCD #3 - Perform exploratory excavation of Dixie Highway for installation of proposed sewer water tie-ins, and determine whether there is sufficient space for the placement of our sanitary structure. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5270 | 0 | 0
7 | 12B-2 | 2002-08-21 | -10000 |  |  |  | U | COPR #4 - Install victaulic couplings in lieu of welded pipe for the chiller system. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0
8 | 12B-8 | 2002-08-21 | 5302 |  |  |  | S | CCD #4 - Provide and install four coats of floor wax to all the floors in the facility. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5302 | 0 | 0
9 | 12B-9 | 2002-12-11 | 3173 |  |  |  | Z | CCD #5 - Install a roof over the exterior kitchen garbage can wash facility. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3173
| 12B-10 | 2003-01-22 |  |  |  |  | - | Reduction of Retainage from 10% to 5%. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-17 | 2003-09-17 |  |  |  |  | - | Reduction of Retainage from 5% to 1% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-7 | 2004-12-08 |  |  |  |  | - | Reduction of Retainage from 1% to 0% and Final Payment and Final Acceptance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 146994 | 5 | 0 | 0
|  | ORIG SUM | 7607700
|  | REV SUM | 7754694
|  | % CO'S | 1.932% |  |  | 0%
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | 0% |  |  | M = Mandatory | 0 | 0%
C = Contractor Suggested |  |  | 0 |  | 0% |  |  | P = Principal Requested | 0 | 0%
D = Design Omission |  |  | 0 |  | 0% |  |  | S = School District Requested | 150061 | 1.972%
E = Design Error |  |  | 0 |  | 0% |  |  | U = Unforeseen Condition | -6240 | -0.08202%
L = Liquidated Damages |  |  | 0 |  | 0% |  |  | Z - Outside Agency | 3173 | 0.04171%