## A
BOCA RATON MIDDLE SCHOOL
MODERNIZATION PROJECT
PROJECT #1491-8379
HISTORY:
2004-01-21 | Board Report 13D-3 fo a Design Re-use Agreement with Zyscovich Inc., in the amount of $875,230.00
TBD | Notice-to-Proceed | [7 empty] | ATTACHMENT
TBD | Original Contract Days
TBD | Original Substantial Completion | [7 empty] | Board Report 12C-1
TBD | Original Final Completion | [7 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD) |  |  | 30
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  | A | C | D | E | L | M | P | S | U | Z
| 12C-4 | 2004-05-19 |  |  | 47300 |  |  | Additional Architectural Services for plan modifications to the Administration area, science labs, group toilets, ESE suite and second floor classrooms. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-1 | 2004-12-08 |  |  | 19060 |  | S | Additional Architectural Services for plans preparation, permitting, construction services. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 0 | 0 | 66360 | 0
|  | ORIG SUM | TBD |  | 875230
|  | REV SUM | 0 |  | 941590
|  | % CO'S | #DIV/0! |  | 7.582% | #DIV/0!
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | #DIV/0! |  |  | M = Mandatory | 0 | #DIV/0!
C = Contractor Suggested |  |  | 0 |  | #DIV/0! |  |  | P = Principal Requested | 0 | #DIV/0!
D = Design Omission |  |  | 0 |  | #DIV/0! |  |  | S = School District Requested | 0 | #DIV/0!
E = Design Error |  |  | 0 |  | #DIV/0! |  |  | U = Unforeseen Conditions | 0 | #DIV/0!
L = Liquidated Damages |  |  | 0 |  | #DIV/0! |  |  | Z = Outside Agency | 0 | #DIV/0!