## A
FOREST HILL COMMUNITY HIGH SCHOOL
MODERNIZATION PROJECT
0581-8215
HISTORY:
2001-03-28 | Board Report 13D-6 for the negotiated Architectural Consultant Agreement with Schenkel Shultz Architecture in the amount of $1,060,000.00.
2001-12-12 | Board Report 13D-1 for an Agreement for CM@ Risk Services and Pre-Construction fees of $197,819.00 to James A. Cummings.
2002-06-26 | Board Report 13D-1 for Amendment #1 to the Agreement eatablishing the GMP of $41,828,887.00 to James A. Cummings, Inc.
2003-06-12 | Notice-to-Proceed
538 | Original Contract Days
2004-12-01 | Original Substantial Completion
2004-12-31 | Original Final Completion
0 | Extensions to Date | [7 empty] | ATTACHMENT
18 | Extension this item
2004-12-19 | Adjusted Substantial Completion | [7 empty] | Board Report 12B-9
2005-01-18 | Adjusted Final Completion | [7 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD)
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  | A | C | D | E | L | M | P | S | U | Z
| 12B-2 | 2002-10-16 |  |  | 298625 |  | S | Additional Architectural Services for the design of the athletic complex and redesign of the existing retained facilities per the Castaldi report to comply with SDPBC education specification requirements; redesign of prototype to incorporate retained facilities, redesign of prototype to accommodate reduced student station count and accommodate new revised academic programs. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-2 | 2002-10-16 |  |  | 15196 |  | Z | Additional Architectural Services to design new water main and route. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-3 | 2003-02-19 |  |  | 32140 |  | Z | Additional Architectural Services for the design of the shared parking with the City of West Palm Beach Golf Club. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-3 | 2003-02-19 |  |  | 14940 |  | S | Additional Architectural Services redesign of the Engineering Technology program of the first floor into a Construction Career Academy as approved by the SDPBC Board. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-9 | 2004-04-21 |  |  | -23950 |  | S | Additional Architectural Services to reduce approved Design Amendment approved on February 19, 2003. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-9 | 2004-04-21 |  |  | 4020 |  | Z | Additional Architectural Services to terminate existing utilities located in the Forest Hill Blvd. Right-of-Way, per the City of West Palm Beach Public Utilities Department permit dated October 17, 2002. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12C-9 | 2004-04-21 |  |  | 1820 |  | U | Additional Architectural Services to design a new roof deck support system for the existing roof on Building #5. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 12C-5 | 2004-05-19 | 129302 |  |  |  | S | CCD #1 - Incorporates various changes, which are added scope, into the renovation of existing Building #2, which are associated with the Environmental Sciences Lab. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129302 | 0
1 | 12C-5 | 2004-05-19 | 84085 |  |  |  | S | CCD #2a - Addition of a Construction Academy Facility in Building #6. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84085 | 0
1 | 12C-5 | 2004-05-19 | 75490 |  |  |  | U | CCD #2b - Relocate the electrical and mechanical room on the second floor of Building #2. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75490
1 | 12C-5 | 2004-05-19 | 68051 |  |  | 68051 | D | CCD #2c - Incorporate revisions to the drawings based on Building Department comments. |  |  | 0 | 0 | 68051 | 0 | 0 | 0 | 0 | 0 | 0
2 | 12B-9 | 2004-06-23 | 0 | 66 |  |  | D | COPR #1 - revise the Phase I Substantial Completion date from a Substantial Completion date of 08/01/03 - 10/06/03 and add $0.00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 12B-9 | 2004-06-23 | 11098 |  |  |  | S | CCD #3 (Item #1) - Added phone conduit. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11098 | 0
2 | 12B-9 | 2004-06-23 | 133545 |  |  |  | U | CCD #3 (Item #2) - Exceeded GMP allowance to re-feed existing campus power systems. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133545
2 | 12B-9 | 2004-06-23 | 147564 |  |  |  | S | CCD #3 (Item #3) - Wiring and termination of the campus intercom and fire alarm re-feed. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147564 | 0
2 | 12B-9 | 2004-06-23 | 1402 |  |  |  | S | CCD #3 (Item #4) - Modify existing Music Room Teacher Planning into a temporary Clinic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1402 | 0
| 12C-2 | 2004-09-22 |  |  | 4200 |  | P | Additional Architectural Services to provide additional services for the design of the renovation of the existing concession stand, which is to be renovated. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12B-9 | 2004-12-08 |  | 18 |  |  | U | CCD #4 - Extend the Phase II and Phase III construction schedule by an additional 18 days. Revise the Substantial Completion date for Phase II and Phase III from December 1, 2004 to December 19, 2004. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 650537 | 84 | 346991 | 68051
|  | ORIG SUM | 42026706 |  | 1060000
|  | REV SUM | 42677243 |  | 1406991
|  | % CO'S | 1.548% |  | 32.73% | 0.1619%
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | 0% |  |  | M = Mandatory | 0 | 0%
C = Contractor Suggested |  |  | 0 |  | 0% |  |  | P = Principal Requested | 0 | 0%
D = Design Omission |  |  | 68051 |  | 0.1619% |  |  | S = School District Requested | 373451 | 0.8886%
E = Design Error |  |  | 0 |  | 0% |  |  | U = Unforeseen Condition | 209035 | 0.4974%
L = Liquidated Damages |  |  | 0 |  | 0% |  |  | Z - Outside Agency | 0 | 0%