## A
WILLIAM T. DWYER HIGH SCHOOL
WEIGHT TRAINING FACILITY PROJECT
PROJECT #2201-8341
HISTORY:
ATTACHMENT
Board Report 12B-3
2003-10-15 | Board Report 13D-4 for Award of Construction Contract to Coral Tech Associates, Inc. in the amount of $309,400.00 | [7 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD) |  |  | 30
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  | A | C | D | E | L | M | P | S | U | Z
1 | 12B-3 | 2004-12-08 | 3540.42 |  |  |  | S | CCD #1 - Install ceramic floor and wall tile in the two restrooms at the new Weight Room Facility. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3540.42 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 3540.42 | 0 | 0 | 0
|  | ORIG SUM | 309400
|  | REV SUM | 312940.42 |  | 0
|  | % CO'S | 1.144% |  | 0% | 0%
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | 0% |  |  | M = Mandatory | 0 | 0%
C = Contractor Suggested |  |  | 0 |  | 0% |  |  | P = Principal Requested | 0 | 0%
D = Design Omission |  |  | 0 |  | 0% |  |  | S = School District Requested | 3540.42 | 1.144%
E = Design Error |  |  | 0 |  | 0% |  |  | U = Unforeseen Conditions | 0 | 0%
L = Liquidated Damages |  |  | 0 |  | 0% |  |  | Z = Outside Agency | 0 | 0%