## A
PALM BEACH GARDENS HIGH SCHOOL
NEW BASEBALL FIELD PROJECT
PROJECT #1371-8340
HISTORY:
2003-05-21 | Board Report 13D-6 for award of contract to Anderson Moore Corporation, Inc. in the amount of $873,948.00
2003-07-28 | Notice-to-Proceed
130 | Original Contract Days
2003-11-04 | Original Substantial Completion | [7 empty] | ATTACHMENT
2003-12-04 | Original Final Completion
2004-09-25 | Actual Substantial completion | [7 empty] | Board Report 12B-5
2004-10-25 | Actual Final Completion | [7 empty] | 2004-12-08
| Board | Board | Dollar | # | Additional | Errors | Cause | Construction Change Directive (CCD)
CO # | Item | Date | Amount | Days | Services | Omissions | Code | Change Order Proposal Request (COPR) |  |  | A | C | D | E | L | M | P | S | U | Z
1 | 12B-7 | 2003-10-15 | 30134 |  |  |  | U | CCD #1 - Furnish and install an additional 4,884 cubic yards (CY) of fill to backfill the two sludge-drying beds. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30134 | 0
2 | 12B-8 | 2003-10-15 | 117685 |  |  |  | S | CCD #2 - Construction of a concession structure, press box, storage, and restrooms. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117685 | 0 | 0
3 | 12B-3 | 2004-05-19 | 2969 |  |  |  | U | CCD #4 - Provide site survey and easement documentation for FPL’s new transformer. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2969 | 0
3 | 12B-3 | 2004-05-19 | 10618 |  |  |  | U | CCD #5 - Construct a dumpster enclosure as required by the City of Palm Beach Gardens. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10618 | 0
3 | 12B-3 | 2004-05-19 | 433 |  |  |  | S | CCD #6 - Add drain line for the icemaker in the Concession Building. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 0 | 0
3 | 12B-3 | 2004-05-19 | 15689 |  |  | 15689 | E | CCD #7 - Install pipe deflections as required by Seacoast Utilities. |  |  | 0 | 0 | 0 | 15689 | 0 | 0 | 0 | 0 | 0 | 0
4 | 12B-5 | 2004-12-08 | 45582.55 | 72 |  | 45582.55 | D | CCD #8 - Extend contract Seventy-two (72) days and extended General Conditions due to the Civil Engineer’s (Metric Engineering, Inc.) failure to get necessary approvals from Seacoast Utility Authority. |  |  | 0 | 0 | 45582.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 12B-5 | 2004-12-08 | 11873 |  |  |  | S | CCD #9 - Site work scope changes and additions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11873 | 0 | 0
4 | 12B-5 | 2004-12-08 | -8132 |  |  |  | S | CCD #10 - Returned unused Portion of Owner Allowance . |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8132 | 0 | 0
| 12B-5 | 2004-12-08 |  |  |  |  | - | Reduction of Retainage from 10% to 0%, Final Payment and Final Acceptance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTALS | 226851.55 | 72 | 0 | 61271.55
|  | ORIG SUM | 873948 |  | 25000
|  | REV SUM | 1100799.55 |  | 25000
|  | % CO'S | 25.96% |  | 0% | 7.011%
CODE LEGEND |  |  | DOLLAR AMOUNT |  | CODE % |  |  | CODE LEGEND | DOLLAR AMOUNT | CODE %
A = Architect Suggested |  |  | 0 |  | 0% |  |  | M = Mandatory | 0 | 0%
C = Contractor Suggested |  |  | 0 |  | 0% |  |  | P = Principal Requested | 0 | 0%
D = Design Omission |  |  | 45582.55 |  | 5.216% |  |  | S = School District Requested | 121859 | 13.94%
E = Design Error |  |  | 15689 |  | 1.795% |  |  | U = Unforeseen Conditions | 43721 | 5.003%
L = Liquidated Damages |  |  | 0 |  | 0% |  |  | Z = Outside Agency | 0 | 0%