Memorandum of Understanding

Regarding Participation in the Research Phase of the

Academic Instruction for After-School Programs Study

SCHOOL DISTRICT OF PALM BEACH COUNTY

# This Memorandum of Understanding describes the Research Phase of the Academic Instruction for After-School Programs Study and the terms and conditions under which The School District of Palm Beach County  (Florida) operating in five elementary schools agree to participate in the research phase of this project.   West Gate Elementary School will be using the new after-school curriculum in math developed by Harcourt School Publishers. Pleasant City, Village Academy, South Grade, and Westward Elementary Schools will be using the after-school reading program developed by Success for All Foundation.

The After-School Impact Study

The U.S. Department of Education has commissioned the Academic Instruction for After-School Programs Study (“After-School Study”) to evaluate whether after-school programs can significantly boost reading and math proficiency of students in grades two-to-five using a curriculum designed specifically for the after-school environment. The Department has contracted with the Success for All Foundation to adapt its Success for All reading program and with Harcourt School Publishers to adapt Harcourt Math and Intervention materials for use in this study.

The study team includes MDRC, Bloom Associates, Public/Private Ventures, and the Survey Research Management. MDRC (www.mdrc.org) is a non-profit and non-partisan research organization in New York and Oakland that is experienced in conducting rigorous and objective studies aimed at enhancing the effectiveness of education and other social policies and programs. MDRC is responsible for evaluating the impact of the enhanced academic curricula during school year 2005-2006. Attachment A summarizes the evaluation plan.  Bloom Associates is responsible for implementation of the after-school curriculum at each of the 50 study after-school centers during the full demonstration in 2005-2006. Public/Private Ventures and the Survey Research Management will be assisting MDRC in collecting and analyzing the evaluation data. The study team is conducting the project for the U.S. Department of Education’s Institute of Education Sciences.

Academic Curriculum Provided for the Research

The academic curriculum to be used by after-school centers in the study is based on curricula now in use during the school day. These materials were pilot tested in 8 sites during the 2004-2005 school year. The curriculum contains the following features:

- Materials consistent with evidence-based research on effective models for reading/math improvement;

- Student assessment integral to the program;

- Content geared to struggling students at multiple grade and/or skill levels;

- Instruction in small group format, in classes of approximately 10:1 student: teacher ratio;

- Lessons of 45-minute duration;

- Curriculum that can complement the in-school instruction but does not depend upon coordination with in-school lessons or materials;

- Content and delivery that is fast-paced and engaging;

- Materials that are appropriately challenging and tied to standards;

- Lessons that are appropriate for students from diverse economic and cultural backgrounds; and

- Instruction that recognizes the limited amount of time that after-school staff can devote to preparation.

Harcourt School Publishers’ After-school Program for Math is a comprehensive and balanced mathematics curriculum. It is built around five mathematical strands: Numbers and Operations; Measurement; Geometry; Algebra and Functions; and Data Analysis and Probability. This interactive program includes games, hands-on activities, projects, and centers, as well as paper-and-pencil practice and applications.  Students use a Daily Fitness Plan to guide them through their activities. These activities include warm-up problem solving activities; focused instruction and practice in math skills; spiral review and test preparation; board and card games; multi-day projects for application of math skills; and vocabulary activities. The program offers computer activities for guided instruction, practice, or enrichment. Pretests are available to help the teacher individualize instruction, and posttests monitor progress.

Adventure Island, published by Success for All Foundation is adapted from its existing reading programs, Reading Roots and Wings. The curriculum for students at the 1st grade reading level focuses on providing students with a strong and comprehensive base for literacy with FastTrack Phonics and Shared Story lessons.  FastTrack Phonics is a fast-paced and systematic phonics program that builds students’ skills in phonemic awareness, letter-sound correspondence, word-level blending and segmenting. During Shared Story lessons students read progressively more complex, engaging and interesting stories with guidance from the teacher, with partners, and finally individually. At the 2nd grade and above, the after-school curriculum utilizes Treasure Hunts, which are lessons based on authentic fiction and nonfiction texts that provide instruction in vocabulary, advanced phonics, fluency, reading comprehension strategies, and story elements. Brief video segments help the teacher model critical tasks. A key component of the curriculum is its comprehensive assessment model.

Responsibilities of the Study Team and of the Participating School Districts and After-School Programs

Major responsibilities and expectations for both the Study Team and for participating school districts, after-school programs, and individual study centers are listed below.

THE AFTER-SCHOOL STUDY TEAM AGREES TO:

- Provide school districts with help in strengthening the academic component of their after-school programs, as evidenced in items listed below.

- Provide after-school programs with free copies of the new curriculum

  - Materials will include everything needed to implement the instruction: teacher guides, student materials, software, etc.

  - Sites can keep these materials even after the research ends

  - Each study center will receive materials and support to serve approximately 50 children.

- Provide professional development conferences for after-school teachers:

  - Two-day professional development conference on September 7-8, 2005 for teachers providing after-school instruction, plus one permanent substitute for each after-school center

  - All costs of travel and substitute teachers (if needed) will be covered by the study team.

- Pay for a part-time school-based Coordinator with responsibility for helping to implement the new curriculum in after-school centers.

  - A list of the tasks and responsibilities of this Coordinator is provided in Attachment B.

  - The study team will train this person (1 day in the summer of 2005 on site, 3 days at the Fall training conference—September 7-9; 2-days at the Mid-Year Meeting in January).

- Provide on-going technical assistance to support implementation of the new curriculum. This includes:

  - Two on-site visits by Bloom Associates and the curriculum developers;

  - Weekly phone meetings with the Coordinator; and

  - Access to curriculum developers and study team members, as needed by phone or email.

- Keep all student information strictly confidential, only making the information available among the Team for the purposes of research and refining the curriculum, training, and technical assistance.   All members of the Study Team sign data confidentiality agreements.

THE SCHOOL DISTRICT AND AFTER-SCHOOL PROGRAMS AGREE TO:

- Identify a District Point Person to be the key contact at the district level responsible for the Research Phase of the Academic Instruction for After-school Programs Study.

  - The District will assume the cost of sending this person to the September 2005 and January 2006 training conferences.

  - The District Point Person will coordinate the on-site visits by Bloom Associates, the curriculum developers, and the research team.

  - He/she will participate in the weekly phone calls (1 for reading, 1 for math) with the school-based Coordinators, Bloom Associates, and the curriculum developers.

  - The District Point Person will supervise the work of the school-based Coordinators, in coordination with Bloom Associates

- Identify candidates for the positions of After-School Reading and Math Coordinators/Curriculum Coaches.

- This is a part-time position, funded by the study team.

- The remainder of this person’s time will be spent as Literacy or Math Coach in the elementary school.

- Bloom Associates will interview the candidates and clarify the roles and responsibilities before finalizing the arrangement.

- Participating school districts and after-school programs will assure that the Coordinator is able to devote 4 hours during the school day and 6 hours after-school to meet the responsibilities of this position (described in Attachment B) .

- The Coordinator will work under the direction of Bloom Associates and the District’s point person responsible for the Research Phase of the Academic Instruction for After-school Programs Study.

- Make the Coordinator available for one day of training on-site in the summer of 2005, three days of training in September 2005, and a 2-day Mid-Year Meeting in January 2006.

- Recruit/identify staff to teach the new curriculum in the study after-school centers.

- Identify an appropriate employee to serve as the After-school Data Collection Coordinator for each school.

- This is a part-time hourly position, as outlined in Attachment C.

- The District will assume the usual costs of operating the after-school program, including paying the teachers. Teachers will be paid for 45-minutes to one-hour of instruction using the SFA Reading or Harcourt After-school Math curriculum and 45-minutes of preparation per day for four days of instruction each week.

- Release the after-school teachers who will use the new curriculum so that they can attend a two-day training in September and professional development session during two on-site visits during the year.

- If the site is chosen to test attendance incentives, the staff will implement the plan which will consist of individual prizes and classroom rewards for excellent attendance. The study team will ask half of the after-school programs to implement the incentives and will provide funding to cover the cost of the plan. All sites will attempt to maximize student participation in the enhanced academic instruction.

- Work to recruit and enroll students in grades 2-5 who are not meeting local academic standards, who will receive either the enhanced academic instruction (the Program Group) or the regular after-school services (the Control Group), according to the research plan shown in Attachment A.

- Inform parents/guardians about the study and the opportunity to enroll their children in the program and receive strengthened academic instruction, the importance of consistent attendance, and any special attendance incentives. The study team will assist center staff in informing parents/guardians of these topics and the existence of the study and its data collection procedures by providing enrollment materials, including a brief study application form, a written consent form to be signed by parents/guardians of participating students, and a contact information form.

- Provide the study team access to the school district data listed in Attachment A and cooperate in the collection of additional research data.

Compensation

In keeping with the Memorandum of Understanding, Bloom Associates agrees to compensate the District in the amount of $13,449 to cover the cost of each of the After School Reading and Math Coordinators at five schools. This assumes 12 hours per week during the school year, plus an additional 56 hours prior to the start of school. The total grant will be $67,245. Three equal payments of $22,415 will be made on November 15, February 15, and June 15.

Survey Research Management will provide pay the Data Collection Coordinators  $ 24.12/hour on a consulting basis.

In addition, upon submission of an invoice, we will also reimburse the District for any substitute teachers required during training.  Travel costs to training sessions will be paid directly by the study team, except for incidentals (parking, etc.) that will be submitted for reimbursement to Bloom Associates.

Signatures

The following people have read this Memorandum of Understanding and agree to the terms and conditions of participation.

Arthur C. Johnson, Superintendent, The School District of Palm Beach County 	    Date

Thomas E. Lynch, School Board Chair						    Date

Ann Killets, Chief Academic Officer							   Date

Signature of Legal Services Designee						    Date

Alison Adler, Chief of Safety and Learning Environment                                             Date

Keith Oswald, Principal, South Grade Elementary School 	      		               Date

Thais Villaneuva, Principal, West Gate Elementary School    	                           Date

Andrea Peppers, Principal, Pleasant City Elementary School                                     Date

Katherine Vaughn-Harden, Principal, Westward Elementary School		    Date

Tammy Ferguson, Principal, The Village Academy Elementary  School		    Date

________________________________________________________________

Fred Doolittle, MDRC 						                        Date

________________________________________________________________

Susan Philipson Bloom, Bloom Associates                                                      Date

ATTACHMENT A.

RESEARCH REQUIREMENTS

Student Recruitment for the Study

- After-school program staff will recruit students in grades two through five for the study who are not currently meeting local academic standards.

- The students in the study sample will be drawn from students who apply for and are admitted to the after-school program in the study after-school centers.

- As part of the after-school program recruitment and application process, program staff will provide information on the study to parents/guardians using the project description and informed consent form developed by the study team.

- After-school program staff will include the study application form and contact sheet in the application materials for the after-school program.

- For each after-school center included in the study, the project can provide  curricular materials and support to serve approximately 10-13 students in each of grades two through five, for a total of approximately 40-52 children.

- After-school program staff will work with the study team to identify a study sample of students that is approximately twice as large as can be served in the enhanced academic classrooms. Students in this study sample will meet the following requirements:

  - Students are attending the after-school program in the fall of 2005

  - Parents/guardians have signed an informed consent form stating they understand the study procedures and agree for their child to be part of the study and this form has been provided by the study team;

  - Parents/guardians have provided contact information to facilitate follow up data collection and this form has been provided by the study team;

  - Parents/guardians have completed the study application form and this form has been provided by the study team; and

  - Students have completed the baseline achievement test(s) administered by the after-school program staff and the study team, as described in the Data Collection section of this Attachment.

- The identification of this study sample will be completed no longer than one month after the start of the after-school program.

CREATION OF A PROGRAM AND CONTROL GROUP THROUGH USE OF A LOTTERY

- The study team will randomly assign students in the study sample to either the program group (which will receive instruction using the enhanced curriculum) or the control group (which will continue to receive the usual after-school program services which may include the fee-based program—SACC—or the Beacon program, at no charge. None of the control youth will participate in CHAMPS.)  Random assignment is similar to a lottery or drawing where all students in the study sample have the same chance of being selected to receive the special instruction.

- The study team will quickly conduct the lottery as soon as the study sample is identified. Only the study team will determine whether a student is assigned to the program group or to the control group.

- The after-school program staff and study team will develop procedures to inform student and parents/guardians of the results of this lottery and the services to be offered each group of students.

- Throughout school year 2005-2006, the after-school program staff will provide services to students based on the results of the study lottery,

- The program staff will do everything possible to ensure good attendance by students in the program group who are receiving the enhanced curriculum.

- The program staff will avoid providing members of the control group the special instruction. In order to fill any vacancies that may exist during the year, only students who are not part of the study sample may be added to the classes using the new curriculum.

Data COllection for the Study

Data collection for the study will be conducted as outlined in the Data Collection Summary Chart on the following page.  This chart lists the key data sources, the reason for collecting the data, the staff involved in collecting the data, and the timing of data collection.

| Academic Instruction for After-School Programs Study: DATA COLLECTION SUMMARY CHART |
| --- |
| Data Source | Objective of Data Collection | Nature of Data Collected | Staff Involved in Collecting Data | Timing of Data Collection |
| Parent/guardian study application form | Characteristics of the students in the study sample | Basic background information on students and their family circumstances | After-school program staff include application in the materials used to recruit students for the program | Summer and fall of 2005, prior to random assignment. |
| Parent/guardian contact information | Facilitate follow-up data collection (student and teacher survey, and achievement testing) if the study is not attending the after-school program in the spring of 2006. | Contact information such as listing of relatives who will know where the family lives, should they move. In addition, school district records on addresses and transfers across schools and districts. | Parent/guardian fills out short form as part of application. Study Data Collection Coordinator works with school district to update contact information for students not attending after-school program. | Initial contact information collected at application in summer/fall of 2005. Updated during school year 2005-2006. |
| Baseline testing of student achievement | Initial academic achievement of students in the study sample | Approximately 60 minute group-administered test of reading or math achievement, using standardized test. | After-school Data Collection Coordinator will work with after-school program staff to conduct tests. Study team will collect and arrange for scoring of the tests. | Fall of 2005 at the start of the after-school program, prior to random assignment of the study sample. |
| After-school program attendance data | Extent of participation in the overall after-school program and in the enhanced instruction using the new curriculum. | Daily attendance for each student in the study sample. | After-school program staff take attendance daily as part of the usual operations of the program. Data provided weekly to the District Coordinator. | Weekly throughout the school year. |
| Field research and observation of after-school program and brief staff survey | Characteristics of the services received by the program and control groups and issues in implementing the curriculum. | Information on the local context, services offered in the after-school programs, implementation of the enhanced curriculum, implementation lessons. | After-school program staff will be interviewed and surveyed and activities will be observed by study team. | Multi-day field research visit will be scheduled at mutually convenient time in early 2006. |
| Student survey | Student reactions to the academic support provided by the after-school program and information on other out-of-school academic support they may be receiving. | Information on how students in the program and control group experience the academic support after-school program (engaging, challenging, different from regular school) and on any other academic support they receive | After-school Data Collection Coordinator will work with program staff to administer the survey to students. Survey takes approximately 5 minutes to complete and will be read to groups of students during after-school time. | December of 2005 and spring of 2006. |
| Regular school day teacher survey | Academic performance of students in the study sample and any special academic support members of the study sample receive during the school day | Teacher assessment of the academic performance of students and listing of any special, individualized support students received during the school day. | After-school Data Collection Coordinator will work with program and school staff to identify regular school day teachers, provide teachers the short survey (approximately 5 minutes), and collect the surveys. | Spring of 2006 |
| Follow-up achievement testing | Academic achievement of students in the study sample at the end of school year | Approximately 60 minute group-administered test of reading or math achievement, using standardized test, plus individually-administered reading tests (for reading sites only) | After-school Data Collection Coordinator will work with after-school program staff to conduct tests Study team will collect and arrange for scoring of the tests. | Spring of 2006 |
| Student academic records | Student academic performance | Grades, attendance, promotion/retention, district-administered test scores | Study team will work with local school district to receive student records in automated format, if possible | Fall of 2006, when records available for school year 2005-2006. |

STUDY RESULTS

Study findings will be presented in written reports and briefings without identifying results for any individual school district or after-school program.  Information on individual students or staff members will not be presented.

The study team will provide school districts and after-school programs participating in the study information on the results for their program in a confidential memo.  It is likely that the sample size in any individual study site will not be large enough to produce statistically significant findings, but these confidential results can be used locally by program administrators.

ATTACHMENT B.

TASKS AND RESPONSIBILITIES:

FOR AFTER-SCHOOL READING or MATH COORDINATORS

OVERALL:

- Serve as the primary point of contact between the District and the participating schools to ensure that all needed supports are being provided

- Work under the direction of Bloom Associates and the District’s point person responsible for the Research Phase of the Academic Instruction for After-school Programs Study

- The After-School Reading or Math Coordinators will be identified as soon as possible after the Memorandum of Understanding is signed; they will be ready to participate in the summer site visit in June.

PLANNING AND START-UP TASKS:

- Work with the principal and after-school programs/centers to recruit and select after-school staff for academic instruction. Provide candidates with information about the curriculum and project expectations.

- Help identify a candidate to serve as the After-School Data Collection Coordinator who will organize and oversee the baseline and follow-up standardized testing and other data collection.

- Work with the after-school programs to establish a schedule and hours for the academic component of the after-school program. (Instruction will be delivered four days/week, immediately after snacks.)

- Help the after-school programs arrange for classroom space, equipment, computers, etc as required for high quality implementation.

- Together with the study team, help staff at each center/school to develop strategies for recruiting and enrolling students to meet the research sample requirements.

- Together with the study team, work with local staff to develop strategies to encourage and reward student attendance.

- Work with the principal and after-school program staff to develop family information to advertise the availability of the program and obtain informed consent for participation in the research; to encourage regular attendance and to reinforce learning.

- Receive all curricula materials from the curriculum developer and classroom supplies from Bloom Associates.

- Be sure the school arranges for substitutes while teachers are away at training.

- Arrange travel with Bloom Associates, accompany teachers to training, and submit participant expense forms.

- Assist the After-school Data Collection Coordinator to organize and administer the baseline achievement tests for all students in the study sample prior to the lottery.

- Work with the school to notify students, parents, and staff regarding which students will receive the enhanced academic curriculum and which will receive regular after-school services.

ON-GOING TASKS:

- Help after-school program staff establish and maintain a positive learning environment.

- Distribute all curricula materials and supplies to the classrooms; and replenish them, as needed, during the school year.

- Maintain a master set of all curriculum materials.

- For Reading Sites Only: Assume responsibility for the curriculum-related testing component. (This refers to the Word Meaning and Word ID Tests used for initial diagnostics and to form classroom groupings.) If needed, help after-school program staff administer and/or score these reading tests which are provided by the developer as part of the curriculum.

- Use attendance information to monitor which students are participating and refine supports/sanctions to encourage good attendance

- Monitor program operations to be sure that students in the program group are not attending the recreational portions of the after-school program unless they attend the academic classes. Also monitor to be sure that control youth are not attending the enhanced academic classes.

- Spend at least 4 days/week during the after-school hours to:

- Visit classrooms for the full period on a pre-scheduled basis.

- Conduct one full-class observation each week at each after-school center. This will result in seeing every teacher once per month.

  - Visit all classrooms on an informal and unannounced basis each week.

- Schedule time after class or on the day following scheduled observations to provide constructive feedback to instructors.

- Serve as a coach for teachers in the after-school centers to reinforce training and problem solve.

- Teach model lessons in teachers’ classrooms, if needed or requested.

- Serve as a monitor to ensure that the curriculum is being faithfully and fully implemented

  - This will involve completing observation forms prepared by Bloom Associates and the developers

  - Identify any staff members who are not effectively implementing the curriculum and determine whether additional training and support is needed, or if a replacement should be hired

- Provide orientation and training to new staff, in case of turnover.

- Hold weekly meetings of the after-school teachers for the purpose of peer support and additional training. Plan agendas and prepare minutes of the meeting.

- Prepare for and participate in technical assistance phone calls with Bloom Associates and the curriculum developers (approximately 1/week).

- Prepare for and participate in site visits with Bloom Associates and the developers (2/year) and the study field research team (1/year).

- Prepare for and attend Mid-Year Meeting for all sites.  Arrange for attendance by any new staff hired after the September training conferences.

- At the end of the program, collect curriculum materials and surplus supplies for future use.

# REPORTING REQUIREMENTS:

The After School Reading or Math Coordinator will be responsible for obtaining the operational data required for the project.  He/she will work with the Data Collection Coordinator to provide the research data needed, as well.

Specific data reporting responsibilities include:

- Complete regular reports that document participation (attendance) for members of the program group.

- Submit attendance reports to the study team every week, based on an approved system of daily attendance monitoring.

- Submit tracking reports that document students who leave the program and any known information about a new residence or school.

- Submit brief narratives that describe attempts to “recapture” students who stop attending the SFA or Harcourt After-school classes.

- Submit classroom observations for the purpose of continuous improvement efforts.  Checklists and rating scales will be developed and provided by the study team to assist in the collection of these observations.

- Provide information to the study team regarding the success and challenges of the new curriculum implementation from a local perspective, in the form of individual discussions, feedback forms, etc.

- Prepare recommendations for curriculum revisions, staff training, and program modifications.

- The Coordinator will be responsible for insuring that the teachers keep careful documentation of student progress, as specified in the curriculum.  This will be explained fully in the September 2005 and January 2006 training sessions.

# QUALIFICATIONS:

Critical skills needed for the position include: experience with elementary grade reading or math instruction; experience serving as a coach or facilitator; strong organizational skills and careful attention to detail; familiarity with the school district policies, personnel, and population served.

ATTACHMENT C

TASKS AND RESPONSIBILITIES

FOR DATA COLLECTION COORDINATORS

Survey Research Management

1495 Yarmouth Avenue Suite A

Boulder, Colorado 80304

303-998-0376

The Data Collection Coordinators will serve as the primary on-site person at each school responsible for research data collection between August 2005 and October 2006. The Coordinator will work under the direction and supervision of Survey Research Management who is responsible for the Data Collection Phase of the After-School Programs Study. He/she will work closely with the After-School Reading and Math Coordinators who are responsible for the successful implementation of the enhanced curriculum at the study centers.

PLANNING AND ON-GOING TASKS:

- District and school staff will provide recommendations for the Data Collection Coordinator position.  Coordinators at all sites will be hired by Survey Research Management by August 1, 2005.

- Survey Research Management will work together with the study team to establish a baseline and follow-up testing and survey schedule and work with all appropriate program staff to coordinate the effort.

- Coordinators will participate in a 1 to 2 day training workshop paid for by Survey Research Management (SRM).   This will occur during the first week of August.

- The Coordinator will work at one after-school program center with approximately 80 students in grades 2-5.

- Together with SRM staff, the Data Collection Coordinator will work with the District Coordinator and local staff to:

- collect and process all program applications, contact information, and consent forms.

- work with local staff to collect current attendance records.

- organize and collect student tests and surveys and teacher surveys.

- locate students who have left the program and whose address is no longer known by the school district.

- collect student records.

- The Data Collection Coordinator will receive and distribute all survey and testing materials and purchase locally-supplied items, as needed.  These locally-supplied incidental items (for example, pencils, envelopes, student snacks,) to be paid for by Survey Research Management. In addition, the Coordinator may be involved in scoring some of the completed tests and/or surveys. He/she will take responsibility for processing and shipping completed tests and surveys to SRM.

- The Data Collection Coordinator will participate in weekly calls with Survey Research Management staff.

- In accepting the position the Coordinator will commit to working the following number of hours per week:

  - August/September-- 10 afternoon hours per week organizing and collecting approximately 80 baseline student tests and student program application forms, contact information, and  consent forms

  - October/November-- 2 hours per week collecting program attendance records and locating students who move

  - December—3 hours per week collecting program attendance records, locating students who move, and administering approximately 80 student surveys.

  - January-March 2006—2 hours per week collecting program attendance records and locating students who move

  - April/May—7 hours per week organizing and administering follow-up student tests and surveys (approx 80 students) and teacher surveys (approx. 24 teachers).

  - September/October they will work a total of 10 hours with the schools to obtain student records and ship them to Survey Research Management.

SKILLS REQUIRED:

- Critical skills necessary for the position include strong organizational skills, proven record following direction with good comprehension, attention to detail, conscientious, strong problem solving skills, ability to work independently, good people skills, dependable, bi-lingual--Spanish speaking may be desirable in some locations.

- Experience working in a school environmental is desirable.

- Experience administering standardized achievement tests is desirable.

COMPENSATION

Data Collection Coordinators will be paid on an hourly basis at the rate of $24.12/hr.